## CONTROLSHEET (hidden)
Yes | 1 | Ordered | 1.1 | 1 - Not Started | No Progress
No | 2 | Voluntary | 2.1 | 2 - Planning for Implementation | Some Progress
| 3 |  | 3.1 | 3 - Beginning Implementation | Significant Progress
| 4 |  | 4.1 | 4 - Partial Implementation | Met
| 5 |  | 5.1 | 5 - Full Implementation
| 6 |  | 5.3
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## DCSI Attestation Stmnt
Osborne ES
2020-2021 District Coordinator of School Improvement (DCSI) Superintendent Attestation
The superintendent must name a District Coordinator of School Improvement (DCSI) if their local education agency (LEA) meets one or more of the following criteria: • the LEA, including those evaluated under alternative education accountability, was assigned an overall rating of F or must engage in unacceptable interventions due to TEC §39A.0545(b) or (c) or was assigned an overall rating of D or D in a domain; • a campus within the LEA, including alternative education campuses, was assigned an overall rating of D or F or D in a domain; • a campus was identified as in need of Comprehensive Support, Targeted Support, or Additional Targeted Support; or • the LEA or campus described above has an appeal of a 2020 accountability rating pending.
The DCSI oversees the work of school improvement as a required member of the Campus Intervention Team (CIT), leads and participates in the needs assessment, including the Effective Schools Framework (ESF) self-assessment and ESF Diagnostic process, improvement planning, and monitoring processes, and ensures requirements and submissions are completed on time. The DCSI supports campus and district improvement by ensuring that the district creates the conditions for campus implementation of best practices. The district commitments in the ESF describe what the district does to create the foundations upon which school-based best practices are built, and the district’s actions are captured in the Targeted Improvement Plan (TIP). The DCSI needs to be in a position to impact and/or influence the ESF district commitments aligned to campus needs. DCSIs are principal supervisors or other district-level leaders with direct responsibility for campuses that have been identified for improvement under state and/or federal accountability. It is strongly encouraged that the DCSI be the supervisor of the principal for the campus with an unacceptable performance rating. If the DCSI is not the principal supervisor, the principal supervisor is required to be a member of the CIT per Texas Administrative Code §97.1063(b)(2). I, the superintendent of schools, attest that I have read the DCSI Job Description, and that the DCSI selected can perform all the duties included in the job description.
DSCI Job Description
Campus Name: | District Coordinator of School Improvement (DCSI) Name, Role:
Osborne ES | Silvia Trinh, Chief of Staff
Campus Number: | Superintendent Name:
213 | Dr. Grenita Lathan
Date:
2020-10-13

## Foundations
CAMPUS INFORMATION
Complete all campus information, including all names for the roles listed. In row 6, please indicate if this Targeted Improvement Plan is the implementation of a Turnaround Plan. If so, please put the school year that the TAP was first implemented. Please indicate if you were ordered to implement the TAP or if implementation is voluntary.
District Name | Houston ISD | Campus Name | Osborne ES | Superintendent | Grenita Lathan | Principal | Mikia J. Barnes
District Number | 101912 | Campus Number | 213 | District Coordinator of School Improvement (DCSI) | Silvia Trinh | ESC Number | 4
Is this a Turnaround Implementation Plan? | No | What Year was the TAP first implemented? |  | Was TAP Implementation Ordered or Voluntary? |  | ESC Support | Sheila Gruever
ASSURANCES
Enter the name of the person in each role below and the date this tab was completed. Please update row 12 with the Board Approval Date when the TIP has been board approved.
DCSI |  | I, the District Coordinator of School Improvement, attest that I will provide or facilitate the provision of all the necessary district-level commitments and support mechanisms to ensure the successful implementation of the Targeted Improvement Plan for this campus. I understand I am responsible for the implementation of all intervention requirements. If I am the principal supervisor, I understand I am responsible for ensuring the principal carries out the plan elements as indicated herein. |  |  |  | Silvia Trinh
Principal Supervisor * Only necessary if the DCSI is NOT the Principal supervisor. |  | I, as supervisor of the principal for this campus, attest that I will coordinate with the DCSI to provide or facilitate the provision of all the necessary district-level commitments and support mechanisms to ensure the principal I supervise can achieve successful implementation of the Targeted Improvement Plan for this campus. I understand I am responsible for ensuring the principal carries out the plan elements as indicated herein. |  |  |  | Stephen Gittens
Principal |  | I, as principal for this campus, attest that I will coordinate with the DCSI (and my supervisor, if they are not the same person) to use the district-provided commitments and support mechanisms to ensure the successful implementation of the Targeted Improvement Plan for this campus. I agree to carry out the plan elements as indicated herein. |  |  |  | Mikia J. Barnes
Board Approval Date
DATA ANALYSIS
Using your accountability data from 2019 (see link in Column G), and any relevant student achievement data from 2019-2020, set reasonable goals in each domain (1, 2B and 3). Include what special student groups you will be monitoring for progress. Include CCMR goals, if applicable. | [5 empty] | https://rptsvr1.tea.texas.gov/perfreport/tapr/2019/index.html
Data Analysis Questions | What accountability goals for each Domain has your campus set for the year? Be sure to include how you determined the goal for each domain and how these goals will impact your overall Accountability Rating. |  |  | Domain 1: For the 2020/2021 school year, our campus will increase our Domain 1 component score from a 28 (scale score of 56) to a 41 (scale score of 70) by increasing student performance in each level: Approaches to 70%, Meets to 36%, and Masters to 16%. This student performance increase will allow our campus to achieve an overall C rating for 2021. Rationale: We have seen other campuses in our district achieve these results, and believe they are feasible for us. By focusing on strong instructional leadership, strong lesson plans, and observation and debrief cycles, we can achieve these results.
Domain 2B: In 2021, we will focus on Domain 2B. Our goal is to reach a component score of 41 (scale 74) specifically for our economically disadvantaged students. Rationale: We have an Economically Disadvantage student percentage of 80%. Focusing on campus relative performance this year, we can demonstrate that our students can achieve at similar or higher levels comparable to other schools with similar demographics.
Domain 3: In 2021, we will increase our Domain 3 score of 31 (scale score of 63) to 50 (scale score of 70). Rationale: Our English Learner population comprises 40% of our student body. Though neither campus subpopulation met the Student Achievement component of this domain, 2020 Texas English Language Proficiency Assessment indicates that our campus continued implementation of differentiated and sheltered instructional strategies will help our English Learner students achieve the English Language Proficiency Standards indicator and perform at Meets level performance band.
| What changes in student group and subject performance are included in these goals? |  |  | Domain 1: All students will receive targeted interventions for math and reading based on deficit skills.
Domain 2B: Students with less than one year's growth will be tracked and targeted so that relative performance can be compared to the same demographics.
Domain 3: We will target sub populations and Special Education populations for Domain 3, along with prioritizing the achievement for our English Learner students.
If applicable, what goals has your campus set for CCMR and Graduation Rate?
CAMPUS FOCUS AREAS
Use information from your Reflective Prioritization Activity and ESF Diagnostic (if available) to complete the following section.
Essential Action |  |  |  |  | Implementation Level (1 Not Yet Started - 5 Fully Implemented)
1.1 Develop campus instructional leaders with clear roles and responsibilities. |  |  |  |  | 4 - Partial Implementation
2.1 Recruit, select, assign, induct and retain a full staff of highly qualified educators. |  |  |  |  | 3 - Beginning Implementation
3.1 Compelling and aligned vision, mission, goals, and values focused on a safe environment and high expectations. |  |  |  |  | 3 - Beginning Implementation
4.1 Curriculum and assessments aligned to TEKS with a year-long scope and sequence. |  |  |  |  | 4 - Partial Implementation
5.1 Objective-driven daily lesson plans with formative assessments. |  |  |  |  | 3 - Beginning Implementation
5.3 Data-driven instruction. |  |  |  |  | 3 - Beginning Implementation
PRIORITIZED FOCUS AREAS
Complete each section below (please refer to your RPA): Essential Action: From the drop-down menu, select 2-3 Essential Actions the campus has selected to prioritize in the 2020-2021 school year. Rationale: Explain the reason(s) this campus chose to focus on these Essential Actions this year. Capacity Building: For each prioritized focus area selected, list any internal/external capacity building efforts or cohorts in which you will participate this year. You can refer to the Vetted Improvement Programs found here: https://texasesf.org/vetted-programs/ Barriers: For each prioritized focus area selected, list the barriers to implementation the campus may face throughout the year. Desired Annual Outcome: For each prioritized focus area selected, create your annual goal that is specific, measurable, attainable, and realistic. District Commitment Theory of Action: For each prioritized focus area selected, list what the district will do to support the campus to achieve its desired annual outcome. Be sure to reference the District Commitments found in the ESF located here: https://texasesf.org/framework/
|  | Prioritized Focus Area #1 |  | Prioritized Focus Area #2 |  | Prioritized Focus Area #3
Essential Action |  | 5.1 |  | 5.3
Rationale |  | Common lesson plan templates are in use across the campus. The Instructional Leadership Team leads the planning process on a weekly basis and all teachers participate in the sessions. Intermediate teachers follow the plans closely. Primary teachers plan together but operate autonomously with regard to lesson delivery. There is a disconnect in the planning process between primary and intermediate grade levels. Daily formative assessments in the form of exit tickets have been introduced at the intermediate level. The instructional team has started the process of looking at exit ticket results on a weekly basis. Lesson objectives were posted in each classroom, but few were measurable objectives. The campus is also focusing on the pacing of lessons. |  | Campus instructional leaders facilitate data review sessions during Professional Learning Community time, with the campus-wide Instructional Leadership Team, and during campus data sessions. The data is used by the administrative team to plan for coaching and professional development for teachers. The data is also used in Professional Learning Community meetings to inform instruction, guide instructional planning and plan for remediation. This planning process is driven by the instructional leadership team. Building teacher proficiency in using data to plan for instruction is an area of growth.
How will the campus build capacity in this area? Who will you partner with? |  | Administrative roles and responsibilities have shifted to content specification. Tier 2 leaders and Teacher Development Specialist will lead content lesson design in all grade levels. Horizontal planning is a campus wide expectation. Vertical planning sessions will also be facilitated for teachers this year. Exit tickets are a campus wide daily expectation that is included on daily lesson plans and will be monitored by administration. |  | Teachers in upper grade levels made significant growth in learning the data disaggregation process and how to identify next steps. This was largely led by administration. This year, primary teachers will be taught the process and upper grade level teachers will be gradually released to independently continue the practice. This shift will be led and monitored by campus administration, Data Driven Instructional Specialist, and Teacher Development Specialist.
Barriers to Address throughout this year |  | Virtual instruction, Technology literacy, Planning and managing work stations both virtually and face-to-face, Teacher capacity to create rigorous formative assessments, Understanding and implementing English Language Proficiency Standards |  | Student goal setting and data conferences
How will you communicate these priorities to your stakeholders? How will you create buy-in? |  | These priorities will be communicated through meetings, planning, Professional Learning Communities, and observation feedback. Teacher leaders on the Instructional Leadership Team will create buy-in by leading professional development, modeling expectations and supporting colleagues with implementation through feedback, collaborative planning and professional development opportunities. |  | These priorities will be communicated through meetings, planning, Professional Learning Communities, and observation feedback. Teacher leaders on the Instructional Leadership Team will create buy-in by leading professional development, modeling expectations and supporting colleagues with implementation through feedback, collaborative planning and professional development opportunities. Also Instructional Leadership Team will create teacher/student celebrations when teacher/student reach their learning goals.
Desired Annual Outcome |  | 100% of teachers will develop in the area of planning which will be indicated by a Teacher Appraisal and Development System score of 3 or higher or an increase, at least, in last year's PL-3 rating. 100% of teachers will participate in horizontal planning as well as strategic planning and alignment sessions. Exit tickets will be implemented daily in 100% of classrooms and the data will be tracked and used to drive next steps for planning and instruction. Lesson and language objectives will be posted daily in 100% of classrooms that are aligned and observed in instructional activitiws for the day. |  | 100% of teachers will be able to identify student misconceptions on formative assessments and implement corrective instruction to increase individual student achievement and growth. 100% of teachers will hold student conferences. 100% of teachers and students will consistently use data tracking tools to track student progress toward learning goals.
District Commitment Theory of Action |  | If the district ensures access to high-quality common formative assessment resources aligned to state standards for all tested areas and PK-2nd grade math and reading and district policies and practices support effective instruction in schools, then, we will reach our state accountability goals. |  | If assessments that are district provided and graded, the district ensures that schools receive detailed reports within two instructional days. The district provides schools with access to student academic, behavioral, and on-track to graduate data (present and historical) then, we will reach our state accountability goals.
DRAFT

## Student Data Tab
|  | Campus Name: | Osborne ES | Campus Number: | 213
STUDENT DATA
To complete the Student Data Tab, please enter data for all STAAR tested courses. - For Domain 1, enter the 2019 STAAR results for each tested course. You can enter the Total % of assessments at Approaches/Meets/Masters for your campus in column H in the form App/Meets/Ma (for example: 60/20/10). If you prefer to enter the data by each grade-level, you may add rows to accommodate each grade. If you administered a baseline assessment, please enter the data from that assessment in Column I. Enter the Total % of tests at each level of proficiency: Approaches, Meets, Masters. For each cycle, please enter Assessment Type. Remember to use comparable, STAAR-aligned assessments for each cycle. Enter the formative goal for that cycle. Once data is available, please update the Actual Result column. Please enter a Summative Goal as well. - For Domain 3, you will choose 2-4 targets to track this year. You can choose 1-2 targets from the Academic Achievement Indicators, 1-2 targets from the Student Success Indicators or a combinations of targets from both areas. Please indicate if you are choosing Academic Achievement or Student Success Indicators in Column B. . Please indicate if you are choosing Academic Achievement or Student Success Indicators in Column B. You will choose which tested subjects to track for these indicators. Your TEA Specialist can support you in selecting these focus areas. Just like in Domain 1, please include the 2019 results for each selected target group. If you administered a baseline assessment, please enter the data from that assessment in Column I. Enter the Total % of tests at each level of proficiency. Please enter a Summative Goal as well. If you are choosing to track Academic Achievement- Track Meets ONLY If tracking Student Success (El/MS) track an average of Approaches, Meets and Masters (as one number) High Schools or K-12 campuses should use one number that is in relation to CCMR. For each cycle, please enter the Assessment Type. Remember to use comparable, STAAR-aligned assessments for each cycle. Enter the formative goal for that cycle. Once data is available, please update the Actual Result column. - You will also track your English Language Proficiency throughout the year. Just like in Domain 1, please include the 2019 TELPAS data. If you administered a baseline assessment, please enter the data from that assessment in Column I. For each cycle, please identify what assessment you are using to track the progress of students (as a proxy for TELPAS). You can adjust the data you provide, based on the data your campus collects. Enter the formative goal for that cycle. Once data is available, please update the Actual Result column. Please enter a Summative Goals as well. Please communicate with your TEA School Improvement Specialist if there are challenges in completing all portions of this data at each cycle due to the disruption of the school year in regard to COVID-19. ** To unfreeze panes, select the View tab and click the Freeze Panes button.
Ple
Core Metrics | Sub Metrics | Grade Level | Student Group | Subject Tested | Performance Level | Summative Assessment | % of Assessments
[7 empty] | 2019 Results | 2020 Baseline Data (Optional) | Cycle 1 |  |  | Cycle 2 |  |  | Cycle 3 |  |  | 2021 Accountability Goal
[9 empty] | Assessment Type | Formative Goal | Actual Result | Assessment Type | Formative Goal | Actual Result | Assessment Type | Formative Goal | Actual Result | Summative Goal
1. Domain 1 | % of Students at Approaches, Meets and Masters | 3rd-5th | All | Reading | Approaches | STAAR | 59 |  |  |  |  | DLA | 63 |  | Released STAAR | 67 |  | 69
|  | 3rd-5th | All | Reading | Meets | STAAR | 39 |  |  |  |  | DLA | 40 |  | Released STAAR | 42 |  | 44
|  | 3rd-5th | All | Reading | Masters | STAAR | 17 |  |  |  |  | DLA | 19 |  | Released STAAR | 21 |  | 22
|  | 3rd-5th | All | Mathematics | Approaches | STAAR | 66 |  |  |  |  | DLA | 70 |  | Released STAAR | 73 |  | 76
|  | 3rd-5th | All | Mathematics | Meets | STAAR | 32 |  |  |  |  | DLA | 37 |  | Released STAAR | 42 |  | 46
|  | 3rd-5th | All | Mathematics | Masters | STAAR | 18 |  |  |  |  | DLA | 22 |  | Released STAAR | 25 |  | 28
|  | 5th | All | Science | Approaches | STAAR | 62 |  |  |  |  | DLA | 67 |  | Released STAAR | 71 |  | 73
|  | 5th | All | Science | Meets | STAAR | 36 |  |  |  |  | DLA | 39 |  | Released STAAR | 42 |  | 45
|  | 5th | All | Science | Masters | STAAR | 9 |  |  |  |  | DLA | 12 |  | Released STAAR | 15 |  | 18
|  | N/A | N/A | Social Studies | Approaches | STAAR | N/A |  |  |  |  | N/A |  |  | N/A
|  | N/A | N/A | Social Studies | Meets | STAAR | N/A |  |  |  |  | N/A |  |  | N/A
|  | N/A | N/A | Social Studies | Masters | STAAR | N/A |  |  |  |  | N/A |  |  | N/A
|  | 4th | All | Writing | Approaches | STAAR | 44 |  |  |  |  | DLA | 48 |  | Released STAAR | 53 |  | 53
|  | 4th | All | Writing | Meets | STAAR | 18 |  |  |  |  | DLA | 22 |  | Released STAAR | 27 |  | 29
|  | 4th | All | Writing | Masters | STAAR | 4 |  |  |  |  | DLA | 8 |  | Released STAAR | 13 |  | 15
2. Domain 3 Focus 1 | Focus 1 Components (Choose two targets in the Academic Achievement or Student Success indicators) | 3rd -5th | Hispanic | Reading | Meets | STAAR | 15 |  |  |  |  | DLA | 21 |  | Released STAAR | 26 |  | 32
|  | 3rd -5th | AA | Mathematics | Meets | STAAR | 13 |  |  |  |  | DLA | 20 |  | Released STAAR | 25 |  | 31
3. Domain 3 Focus 2 | Focus 2 Components (Choose two targets in the Academic Achievement or Student Success indicators) | 3rd -5th | Eco Dis | Mathematics | Meets | STAAR | 30 |  |  |  |  | DLA | 32 |  | Released STAAR | 34 |  | 36
|  | 3rd -5th | SpEd | Reading | Meets | STAAR | 20 |  |  |  |  | DLA | 16 |  | Released STAAR | 17 |  | 19
4. Domain 3 Focus 3 | ELP Component (Minimum 25 students required) | All | English Learners (ELs) | TELPAS | All | TELPAS | 47 |  |  |  |  | ELD 1 | 30 |  | ELD 2 | 33 |  | 36

## Cycle 1 (Sept-Nov)
|  | Campus Name: | Osborne ES | Campus Number: | 213
CYCLE 1 90-DAY OUTCOMES (September - November)
Essential Action: Pre-populates from the 'Foundations' tab. Desired Annual Outcome: Pre-populates from the 'Foundations' tab. For each Prioritized Focus Area, please complete the following sections: Desired 90-Day Outcome: Describe the specific, measurable goal the campus plans to achieve by the end of this cycle for each prioritized focus area. Barriers: For each prioritized focus area selected, list the barriers to implementation the campus may face during this cycle. District Actions for this Cycle: List what the district will do to support the campus to achieve the desired outcome during this 90-day cycle. District Commitment Theory of Action: Pre-populates from the 'Foundations' tab.
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action | 5.1 |  |  | 5.3 |  |  | 0
Desired Annual Outcome | 100% of teachers will develop in the area of planning which will be indicated by a Teacher Appraisal and Development System score of 3 or higher or an increase, at least, in last year's PL-3 rating. 100% of teachers will participate in horizontal planning as well as strategic planning and alignment sessions. Exit tickets will be implemented daily in 100% of classrooms and the data will be tracked and used to drive next steps for planning and instruction. Lesson and language objectives will be posted daily in 100% of classrooms that are aligned and observed in instructional activitiws for the day. |  |  | 100% of teachers will be able to identify student misconceptions on formative assessments and implement corrective instruction to increase individual student achievement and growth. 100% of teachers will hold student conferences. 100% of teachers and students will consistently use data tracking tools to track student progress toward learning goals. |  |  | 0
Desired 90-day Outcome
Barriers to Address During this Cycle
District Actions for this Cycle
District Commitment Theory of Action | If the district ensures access to high-quality common formative assessment resources aligned to state standards for all tested areas and PK-2nd grade math and reading and district policies and practices support effective instruction in schools, then, we will reach our state accountability goals. |  |  | If assessments that are district provided and graded, the district ensures that schools receive detailed reports within two instructional days. The district provides schools with access to student academic, behavioral, and on-track to graduate data (present and historical) then, we will reach our state accountability goals. |  |  | 0
ACTION PLAN
In each row below, list the actions the campus is taking during this cycle to achieve its desired outcomes and address the identified barriers to implementation. For each action step, indicate: - the prioritized essential action it is aligned to, - the start date/end date during this specific cycle, - the resources needed to accomplish this task, - the person(s) responsible for ensuring task is accomplished, - the evidence that will be used to determine progress toward the action step, and - the date evidence will be collected. At the end of each cycle - For each action step: (1) select the progress review status from the drop down menu, and (2) describe what next steps will be taken during the next cycle. For each action that has not been MET, please update column J with necessary adjustments or next steps for this action step.
Action Step |  | Prioritized Essential Action | Start Date/End Date | Resources Needed | Person(s) Responsible | Evidence used to Determine Progress toward Action Step (May be requested by Specialist) | Evidence Collection Date | Progress toward Action Step | Necessary Adjustments / Next Steps
REFLECTION and PLANNING for NEXT 90-DAY CYCLE
At the end of this cycle, please reflect on the implementation of your Targeted Improvement Plan thus far by responding to the questions below. Be sure to explain whether your outcomes and student performance goals were met and why or why not. List any action steps you will carry over to the next cycle and any new action steps you have discovered necessary for the next cycle. Be sure to add these action steps into the next cycle's action plan.
For each of the Prioritized Focus Areas, did you achieve your desired 90-day outcome? Why or why not?
Did you achieve your student performance goals (see Student Data Tab)? Why or why not?
Review the necessary adjustments/next steps column above. What action steps from this cycle will you continue working on in the next cycle? What new action steps do you need to add to the next cycle? |  |  |  | Carryover Action Steps |  |  | New Action Steps
DRAFT

## Cycle 2 (Dec-Feb)
|  | Campus Name: | Osborne ES | Campus Number: | 213
CYCLE 2 90-DAY OUTCOMES (December-February)
Essential Action: Pre-populates from the 'Foundations' tab. Desired Annual Outcome: Pre-populates from the 'Foundations' tab. For each Prioritized Focus Area, please complete the following sections: Desired 90-Day Outcome: Describe the specific, measurable goal the campus plans to achieve by the end of this cycle for each prioritized focus area. Barriers: For each prioritized focus area selected, list the barriers to implementation the campus may face during this cycle. District Actions for this Cycle: List what the district will do to support the campus during this 90-day cycle to achieve the desired outcome. District Commitment Theory of Action: Pre-populates from the 'Foundations' tab.
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action | 5.1 |  |  | 5.3 |  |  | 0
Desired Annual Outcome | 100% of teachers will develop in the area of planning which will be indicated by a Teacher Appraisal and Development System score of 3 or higher or an increase, at least, in last year's PL-3 rating. 100% of teachers will participate in horizontal planning as well as strategic planning and alignment sessions. Exit tickets will be implemented daily in 100% of classrooms and the data will be tracked and used to drive next steps for planning and instruction. Lesson and language objectives will be posted daily in 100% of classrooms that are aligned and observed in instructional activitiws for the day. |  |  | 100% of teachers will be able to identify student misconceptions on formative assessments and implement corrective instruction to increase individual student achievement and growth. 100% of teachers will hold student conferences. 100% of teachers and students will consistently use data tracking tools to track student progress toward learning goals. |  |  | 0
Desired 90-day Outcome | 70% of all teachers will receive a score of 3 or higher in PL-3 on the Teacher Appraisal and Development System , which will result in student academic growth in all content areas. |  |  | 70% of teachers will track student progress of learning goals based on formative assessment, and create an individualized intervention plan to intervene in low performing areas.
Barriers to Address During this Cycle | Designated planning time, Instructional support for planning, Teacher capacity to backwards plan and decompose standards for scaffolding instruction, Unknown impact of COVID-19 |  |  | Campus wide data tracking system, consistent data tracking, accountability/expectations for data tracking, student data conference protocol, Unknown impact of COVID-19
District Actions for this Cycle | District will provide Teacher Development Specialist(TDS) to coach and develop teachers; School Support Officer (SSO) to support principal; Data Driven Instructional Specialist (DDIS) to support campus data disaggregation and planning for instruction and funding for teacher development via Wednesday After-School Professional Development. |  |  | District will provide Teacher Development Specialist(TDS) to coach and develop teachers; School Support Officer (SSO) to support principal; Data Driven Instructional Specialist (DDIS) to support campus data disaggregation and planning for instruction and funding for teacher development via Wednesday After-School Professional Development.
District Commitment Theory of Action | If the district ensures access to high-quality common formative assessment resources aligned to state standards for all tested areas and Pre-Kindergarten - 2nd grade math and reading and district policies and practices support effective instruction in schools, then, we will reach our state accountability goals. |  |  | If assessments that are district provided and graded, the district ensures that schools receive detailed reports within two instructional days. The district provides schools with access to student academic, behavioral, and on-track to graduate data (present and historical) then, we will reach our state accountability goals. |  |  | 0
ACTION PLAN
In each row below, list the actions the campus is taking during this cycle to achieve its desired outcomes and address the identified barriers to implementation. For each action step, indicate: - the prioritized essential action it is aligned to, - the start date/end date during this specific cycle, - the resources needed to accomplish this task, - the person(s) responsible for ensuring task is accomplished, - the evidence that will be used to determine progress toward the action step, and - the date evidence will be collected. At the end of each cycle - For each action step: (1) select the progress review status from the drop down menu, and (2) describe what next steps will be taken during the next cycle. For each action that has not been MET, please update column J with necessary adjustments or next steps for this action step.
Action Step |  | Prioritized Focus Area | Start Date/End Date | Resources Needed | Person(s) Responsible | Evidence used to Determine Progress toward Action Step (May be requested by Specialist) | Evidence Collection Date | Progress toward Action Step | Necessary Adjustments / Next Steps
All teachers will create and submit daily lesson plans that include clear objectives, standards aligned activities, checks for understanding questions and intentional and appropriate vocabulary instruction |  | 5.1 | Dec 2019 - Feb 2020 | Lesson plan template, Texas Essential Knowledge and Skills, Lead4Ward playlist, HUB | Instructional Leadership Team | Agendas, Sign In Sheets | Date of Professional Learning Community or Professional Development
Consistently use a school-wide tracking systems to track progress towards our cycle campus student goals |  | 5.3 | Dec 2020 - Feb 2021 | Campus Data Tracking Tools, Campus Data from State test and district Snapshot 1 | Administration, Classroom Teachers, Data Driven Instructional Specialist | School wide tracking system in place with data from district Snapshot 1 | Bi-Weekly
Data Professional Learning Community over completing Data Protocol after the DLA district Snapshot |  | 5.3 | Dec 2020 - Feb 2021 | Student Data Protocol, Student Grouping Protocol, Individual Student Data by teacher and subject | Instructional Leadership Team and Grade Level Teachers | Professional Learning Community agenda meeting minutes, completed Teacher Data Protocols and Student Grouping Protocols | 2020-02-02
Instructional Leadership Team Meeting to Review Results from first district Snapshot 2 to arrange upcoming Professional Development over low instructional areas |  | 5.3 | Dec 2020 - Feb 2021 | Professional Learning Community agenda, Campus snapshot results, | Instructional Leadership Team | Professional Learning Community agenda meeting Minutes outlining data driven instructional low areas, and campus focus moving forward | 2020-02-26
During leadership team meetings Principal and Instructional Leadership Team will engage in a lesson plan feedback calibration activity to build skill in this area. |  | 5.1 | Dec 2020 - Feb 2021 | Lesson plans brought to meetings; lesson plan look-fors, feedback protocol | Principal and Instructional Leadership Team | Professional Learning Community Agenda, lesson plan calibration walkthrough look fors | Monthly
Facilitate Professional Learning Communities for teachers, focused on data protocols, tools, and expectations. |  | 5.3 | Dec 2020 - Feb 2021 | Campus Data Tracking Tools, Campus Data from State test and district Snapshot 1 | Administration, Classroom Teachers, Data Driven Instructional Specialist | Agendas, Sign In Sheets, Data Tracking Tools | 2020-02-02
REFLECTION and PLANNING for NEXT 90-DAY CYCLE
At the end of this cycle, please reflect on the implementation of your Targeted Improvement Plan thus far by responding to the questions below. Be sure to explain whether your outcomes and student performance goals were met and why or why not. List any action steps you will carry-over to the next cycle and any new action steps you have discovered necessary for the next cycle. Be sure to add these action steps into the next cycle's action plan.
For each of the Prioritized Focus Areas, did you achieve your desired 90-day outcome? Why or why not?
Did you achieve your student performance goals (see Student Data Tab)? Why or why not?
Review the necessary adjustments/next steps column above. What Action Steps from this cycle will you continue working on in the next cycle? What new Action Steps do you need to add to the next cycle? |  |  |  | Carryover Action Steps |  |  | New Action Steps
DRAFT

## Cycle 3 (Mar-May)
|  | Campus Name: | Osborne ES | Campus Number: | 213
CYCLE 3 90-DAY OUTCOMES (March-May)
Essential Action: Pre-populates from the 'Foundations' tab. Desired Annual Outcome: Pre-populates from the 'Foundations' tab. For each Prioritized Focus Area, please complete the following sections: Desired 90-Day Outcome: Describe the specific, measurable goal the campus plans to achieve by the end of this cycle for each prioritized focus area. Barriers: For each prioritized focus area selected, list the barriers to implementation the campus may face during this cycle. District Actions for this Cycle: List what the district will do to support the campus during this 90-day cycle to achieve the desired outcome. District Commitment Theory of Action: Pre-populates from the 'Foundations' tab.
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action | 5.1 |  |  | 5.3 |  |  | 0
Desired Annual Outcome | 100% of teachers will develop in the area of planning which will be indicated by a Teacher Appraisal and Development System score of 3 or higher or an increase, at least, in last year's PL-3 rating. 100% of teachers will participate in horizontal planning as well as strategic planning and alignment sessions. Exit tickets will be implemented daily in 100% of classrooms and the data will be tracked and used to drive next steps for planning and instruction. Lesson and language objectives will be posted daily in 100% of classrooms that are aligned and observed in instructional activitiws for the day. |  |  | 100% of teachers will be able to identify student misconceptions on formative assessments and implement corrective instruction to increase individual student achievement and growth. 100% of teachers will hold student conferences. 100% of teachers and students will consistently use data tracking tools to track student progress toward learning goals. |  |  | 0
Desired 90-day Outcome | 85% of all teachers will receive a score of 3 or higher in PL-3 on the Teacher Appraisal and Development System , which will result in student academic growth in all content areas. |  |  | 85% of teachers will track student progress of learning goals based on formative assessment, and create an individualized intervention plan to intervene in low performing areas.
Barriers to Address During this Cycle | Time management, Day to Day EOY operations, data tracking capacity, virtual instruction, vertical alignment, teacher burnout, Unknown impact of COVID-19 |  |  | Teacher burnout, Teacher capacity to backwards plan to meet student goals, Lack of motivation, Lack of pedagogy, Unknown impact of COVID-19
District Actions for this Cycle | District will provide Teacher Development Specialist(TDS) to coach and develop teachers; School Support Officer (SSO) to support principal; Data Driven Instructional Specialist (DDIS) to support campus data disaggregation and planning for instruction and funding for teacher development via Wednesday After-School Professional Development. |  |  | District will provide Teacher Development Specialist(TDS) to coach and develop teachers; School Support Officer (SSO) to support principal; Data Driven Instructional Specialist (DDIS) to support campus data disaggregation and planning for instruction and funding for teacher development via Wednesday After-School Professional Development.
District Commitment Theory of Action | If the district ensures access to high-quality common formative assessment resources aligned to state standards for all tested areas and PK-2nd grade math and reading and district policies and practices support effective instruction in schools, then, we will reach our state accountability goals. |  |  | If assessments that are district provided and graded, the district ensures that schools receive detailed reports within two instructional days. The district provides schools with access to student academic, behavioral, and on-track to graduate data (present and historical) then, we will reach our state accountability goals. |  |  | 0
ACTION PLAN
In each row below, list the actions the campus is taking during this cycle to achieve its desired outcomes and address the identified barriers to implementation. For each action step, indicate: - the prioritized essential action it is aligned to, - the start date/end date during this specific cycle, - the resources needed to accomplish this task, - the person(s) responsible for ensuring task is accomplished, - the evidence that will be used to determine progress toward the action step, and - the date evidence will be collected. At the end of each cycle - For each action step: (1) select the progress review status from the drop down menu, and (2) describe what next steps will be taken during the next cycle. For each action that has not been MET, please update column J with necessary adjustments or next steps for this action step.
Action Step |  | Prioritized Focus Area | Start Date/End Date | Resources Needed | Person(s) Responsible | Evidence used to Determine Progress toward Action Step (May be requested by Specialist) | Evidence Collection Date | Progress toward Action Step | Necessary Adjustments / Next Steps
Teachers will demonstrate growth in Teacher Appraisal and Development System instructional criteria PL-3 |  | 5.1 | March 2021 - May 2021 | Teacher Appraisal and Development System Resources | Administration, Teacher Development Specialist, Classroom Teachers | Teacher Appraisal and Development System Ratings | 2021-05-01
Teachers will submit effective lesson plans with all necessary components |  | 5.1 | March 2021 - May 2021 | Lesson Plans, Curriculum Documents | Administration, Teacher Development Specialist, Classroom Teachers | Lesson Plans, Teacher Appraisal and Development System Ratings | Weekly
Teachers can independently disaggregate student data for individual leadership data talks |  | 5.3 | March 2021- May 2021 | Student Data, On Track, Renassaince 360, A4E, Campus and District data tracking tools | Administration, Classroom Teachers | Data Tracking Tools, Data Walls | Bi-Weekly
Teachers will use disaggregated student data to determine next steps (enrich, re-teach, or Repsonse To Intervention referral) for students |  | 5.3 | March 2021- | Student Data, On Track,Renassaince 360, A4E, Campus and District data tracking tools | Administration, Data Driven Instructional Specialist, Classroom Teachers | Response To Intervention Referrals, Re-teach Plans, Intervention Groups | Weekly
REFLECTION and PLANNING for NEXT 90-DAY CYCLE
At the end of this cycle, please reflect on the implementation of your Targeted Improvement Plan thus far by responding to the questions below. Be sure to explain whether your outcomes and student performance goals were met and why or why not. List any action steps you will carry-over to the next cycle and any new action steps you have discovered necessary for the next cycle. Be sure to add these action steps into the next cycle's action plan.
For each of the Prioritized Focus Areas, did you achieve your desired 90-day outcome? Why or why not?
Did you achieve your student performance goals (see Student Data Tab)? Why or why not?
Review the necessary adjustments/next steps column above. What Action Steps from this cycle will you continue working on in the next cycle? What new Action Steps do you need to add to the next cycle? |  |  |  | Carryover Action Steps |  |  | New Action Steps
END OF YEAR REFLECTION
Please reflect on the year's implementation of your Targeted Improvement Plan by responding to the questions below. Be sure to explain whether your campus achieved the desired annual outcome for each Prioritized Focus Area and why or why not.
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action | 0 |  |  | 0 |  |  | 0
Desired Annual Outcome | 0 |  |  | 0 |  |  | 0
Did the campus achieve the desired outcome? Why or why not?
DRAFT

## Cycle 4 (Jun-Aug)
|  | Campus Name: | Osborne ES | Campus Number: | 213
CYCLE 4 90-DAY OUTCOMES (June-August)
The purpose of this 90-Day action plan is to prepare for the upcoming school year. The essential actions the campus prioritizes may have changed based on progress made in the school year or based on ESF diagnostic results. Please complete this portion of the plan by reflecting on your campus's progress this year, and identifying your focus areas for next year. This tab serves as the foundation for next year's Targeted Improvement plan. Complete each section below: Essential Action: From the drop-down menu, select 2-3 Essential Actions the campus has selected to prioritize in the 2021-2022 school year. Rationale: Explain the reason(s) this campus chose to focus on these Essential Actions this year. Communication: Describe how you will communicate your priorities to your stakeholders and how you will create buy-in from key stakeholder groups. Desired Annual Outcome: For each prioritized focus area selected, create your annual goal that is specific, measurable, attainable, and realistic. Desired 90-Day Outcome: Describe the specific, measurable goal the campus plans to achieve by the end of this cycle (June-August) for each prioritized focus area. Capacity Building: For each prioritized focus area selected, list any internal/external capacity building efforts or cohorts in which you will participate this year. You can refer to the Vetted Improvement Programs found here: https://texasesf.org/vetted-programs/ Barriers: For each prioritized focus area selected, list the barriers to implementation the campus may face throughout the year. District Actions for this Cycle: List what the district will do to support the campus to achieve the desired outcome during this 90-day cycle . District Commitment Theory of Action: For each prioritized focus area selected, list what the district will do to support the campus to achieve its desired annual outcome. Be sure to reference the District Commitments found in the ESF located here: https://texasesf.org/framework/
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action
Rationale
How will you communicate these priorities to your stakeholders? How will you create buy-in?
Desired Annual Outcome
Desired 90-Day Outcome
How will the campus build capacity in this area? Who will you partner with?
Barriers to Address throughout the year
District Actions for this Cycle
District Commitment Theory of Action
ACTION PLAN
In each row below, list the actions the campus is taking during this cycle to achieve its desired outcomes and address the identified barriers to implementation. For each action step, indicate: - the prioritized essential action it is aligned to, - the start date/end date during this specific cycle, - the resources needed to accomplish this task, - the person(s) responsible for ensuring task is accomplished, - the evidence that will be used to determine progress toward the action step, and - the date evidence will be collected. At the end of each cycle - For each action step: (1) select the progress review status from the drop down menu, and (2) describe what next steps will be taken during the next cycle. For each action that has not been MET, please update column J with necessary adjustments or next steps for this action step.
Action Steps |  | Prioritized Focus Area | Start Date/End Date | Resources Needed | Person(s) Responsible | Evidence used to Determine Progress toward Action Step (May be requested by Specialist) | Evidence Collection Date | Progress toward Action Step | Necessary Adjustments / Next Steps
DRAFT