## Slide 1: Bond Oversight Committee Meeting First Quarter 2014
April 29, 2014

## Slide 2
2007 Bond Update
Completion of major renovations at Cullen MS and Southmayd ES will occur over the next several months, including roof work at both sites
The expansion of Kate Smith ES is moving forward, which is an additional scope of work made possible through program realignments
All work in the 2007 program will be in the closeout phase by the end of 2014

## Slide 3
2012 Bond Planning
Planning is almost complete for all schools in Group 2 of the 2012 bond program.
Group 2 projects include some of the district’s largest high schools – Bellaire, Lamar, Davis, and Yates
Design charrettes are being scheduled
Each school’s first community meeting will be held by the end of the 2nd quarter of 2014
PATs have toured schools in the metro area and across the country to gain a greater knowledge of 21st century features for new HISD schools

## Slide 4
2012 Bond Design
Second round of community meetings held for Group 1 campuses
Community meetings held for 16 schools during first quarter
Group 1 projects are moving out of Schematic Design and into the Design Development stage
Construction scheduled to begin by end of 2014

## Slide 5
Sustainability
HISD is committed to building sustainable schools with eco-friendly design features that serve as learning tools.
Berry Elementary School, a new environmental studies magnet school funded by the 2007 bond program, received a Silver LEED (Leadership in Energy and Environmental Design) certification for its environmental enhancements designed to save energy at the facility.
In Group 1, 3 schools are going for gold certification, 11 are going for silver, and the rest are seeking certification.

## Slide 6
2012 Bond Construction
Waltrip
Swimming pool renovation complete
Next phase of construction to begin 2nd quarter of 2014
Worthing
Construction on new wing underway
North Houston Early College HS
Sewer and main water lines complete
Site work to start 2nd quarter of 2014
South Early College HS
Installation of meter vault and sanitary sewer to start 2nd quarter of 2014

## Slide 7
Districtwide Upgrades
Delmar Fieldhouse
Demolition complete
Site work in progress
Construction to begin 2nd quarter of 2014
Middle School Restrooms
Assessments complete
Design has begun on the Phase 1 projects
Construction will start in the 2nd quarter of 2014
Safety and Security
Priority 1 work (security cameras) is underway
Safety and security assessment of all district facilities complete
CFS working with Threat Assessment Team to review and prioritize districtwide safety improvements

## Slide 8
M/WBE Outreach Events
Workshop Wednesday
  January: “Meet the Contractors” 2012 Bond Event for CMARs, M/WBEs
  February: Introduction of Procurement team: Reviewing current structure
  March: New M/WBE Participation Process Workshop for prospective vendors
Acres Homes Chambers
  Networking Luncheon
Greater Houston Business Procurement Forum
  Houston Community College Auditorium
  Procurement Summit & Business Expo
Government Procurement Connections
  2014 Planning Committee

## Slide 9
M/WBE Outreach Events (continued)
Houston Minority Supplier Development Council
  Strategic Teaming Alliance Committee (STAC) Meeting
HCC-Spring Branch
  How to Do Business with HISD
Interagency Mentor Protégé Program
  Track 2 Graduation Event
Kingdom Builder’s Center
  Contractors College: “Calling All Construction Partners”
Metro Transit of Harris County
  Contractor Workshop
  Government Procurement Connections Planning Committee Meeting

## Slide 10
2007 Bond M/WBE Participation
Exceeded minimum M/WBE goal levels of 20% for 2007 bond program
M/WBE participation has reached nearly 35% in 2007 bond program
Chart: Total Combined Projects* Total Awarded: $983,541,861 Total Committed: $338,040,860
Chart: 2007 Total Combined Projects Total Awarded: $1,010,362,076 Total Committed: $346,590,827
| MBE | WBE | Non-M/WBE
Sub Total | 231437005.7956 | 115153822.45 | 663771248.4444

## Slide 11
2012 Bond
M/WBE Commitment
Certified Minority/Women Owned Businesses Breakdown
Chart: 2012 Professional Service Projects*
 | 0.3611 | 0.149 | 0.5101

## Slide 12
Doing Business
HISD is committed to Supplier Diversity.
Monthly outreach events are being held for minority and women-owned businesses
M/WBE commitments for contracts awarded to date:
  Professional Services represent 51%
  CMARs represent 20% to 40%
Meet & Greets were held at:
  Worthing High School for awarded CMAR (Balfour Beatty)
  Delmar Fieldhouse for awarded CMAR (DivisionOne Construction)
  Waltrip High School for awarded CMAR (Satterfield & Pontikes)
  Nominated for Distinguished Supplier Diversity Award the by the Houston Minority Business Development Agency Business Center

## Slide 13
Chart: 
| Budget | Commitments | Available to complete Projects
Budget Commitments Available to complete Projects | 1176130676 | 1024281933 | 151848743
2007 Bond Financial Report
Total funding of $1,176,130,676
Actual committed of $1,044,546,922 (including encumbrances of $50,594,360 and actual expenditures of $993,952,562)
Uncommitted funding balance of $131,583,754 or 11% of total funding
As of March 31, 2014

## Slide 14
Chart: Total Budget & Commitments
| Funding to Complete Projects | Commitments
Total Budget & Commitments | 1819043747 | 70956253
2012 Bond Financial Report
Chart: Total Bond Referendum = $1,890,000,000 (sales in millions)
As of March 31, 2014
The total for the 2012 Bond Program is $1.89 billion, and the issuance of the bonds has been planned in four sales
Commitments of $115,615,425 (including encumbrances of $75,443,541 and actual expenditures of $40,171,884) leaving $1,774,384,575 of available funding
Chart: Total Bond Referendum $1,890,000,000 (issuance sales in millions)
 | 340 | 700 | 415 | 435

## Slide 15
Communications
HISD is committed to providing timely and accurate information on the 2007 and 2012 bond programs.
Creating and distributing fliers and meeting invitations to key stakeholders for 16 school community meetings
33 blog posts and photo galleries on school community meetings, green school efforts, and community outreach events
More than 30 tweets and Facebook posts highlighting bond activities
Produced 5 videos that show PATs and community participation in design process and school site tours

## Slide 16
Looking Ahead: 2014
By the end of 2014, construction will begin on all remaining schools in Group 1
Between the 2nd and 3rd quarter, all Group 1 schools will have their third community meeting
In the 2nd quarter, Group 2 schools will have their first community meeting and design charrette

## Slide 17
Looking Ahead: 2014 (continued)
In the 2nd quarter, Group 1 projects will transition from SD to DD and will go through a budget/program alignment process
In the 2nd quarter, a design RFQ will be advertised for Group 3
Supplier diversity networking events will be held at bond campuses to encourage community participation