## Slide 1: Bond Oversight Committee Meeting
Second Quarter 2016
July 26, 2016
Notes: Welcome – Derrick Sanders

## Slide 2: Second Quarter Progress
Construction underway at 22 campuses – more than any other time in HISD history
Construction contracts executed: 7, including 1 districtwide project
6 schools to open in August; move-in preparation/furniture delivery underway
Groundbreaking at Yates HS; Topping Out at Wisdom HS
All projects, except Bellaire, to be bid by end of the year
Six new schools to open for 2016-2017
Condit Elementary
Mark White Elementary
North Houston Early College High School
South Early College High School
Mandarin Immersion Magnet School
North Forest Early Childhood Center
Notes: Second Quarter Progress – Derrick Sanders

## Slide 3: Construction Highlights
DeBakey High School for Health Professions
New school for 900 – 1,000 students
Located in Texas Medical Center
Notes: Construction Highlights – Derrick Sanders

## Slide 4: Construction Highlights
New school for 1,000 – 1,300 students
Furr High School
New performing & visual arts school for 750 students
HSPVA
Notes: Construction Highlights – Derrick Sanders

## Slide 5: Construction Highlights
New school for 1,700 – 1,900 students
Wisdom High School
New school preserving significant architecture for 1,800 – 2,000 students
Milby High School
Notes: Construction Highlights – Derrick Sanders

## Slide 6: Construction Highlights
New school for 400 students
North Houston ECHS
Phase 1 complete
Phases 2 ongoing
Worthing High School
Notes: Construction Highlights – Derrick Sanders

## Slide 7: Construction Highlights
New school for 750 students
Mark White Elementary
New school for 750 – 900 students
Mandarin Immersion
Notes: Construction Highlights – Derrick Sanders

## Slide 8: Construction Highlights
New school for 750 students
Condit Elementary
New center for 500 – 600 students
Non bond school
North Forest ECC
Notes: Construction Highlights – Derrick Sanders

## Slide 9: Construction Highlights
All but 1 package currently under contract
All packages to be under construction by end of 2016
Middle School Restroom Renovations
Notes: Construction Highlights – Middle School Restrooms – Andreas Peeples

## Slide 10: Construction Highlights
Middle School Restroom Renovations
Notes: Construction Highlights – Middle School Restrooms – Andreas Peeples

## Slide 11: Doing Business
Office of Business Assistance held and participated in multiple programs to promote HISD business opportunities
M/WBE commitments for contracts awarded to date:
  Architect projects represent 54%
  Construction firm projects represent 23%
  Program management firm projects represent 48%
  Other projects represent 39%
Notes: M/WBE – Alexis Licata

## Slide 12: M/WBE networking events
Workshop Wednesdays
April Delivering Excellent Customer Service
May Achieving Your Desired Results
June: Building Cyber Resilience – Being Proactive in a Reactive Cyber World
Notes: M/WBE – Alexis Licata

## Slide 13: M/WBE outreach events
Greater Houston Black Chamber
U of Houston/TxDOT Forum
Southeast Texas Association of Public Purchasing: Expo/Forum
Women’s Business Enterprise Alliance: Expo/Luncheon
Houston Minority & Supplier Diversity Council
Greater Houston Business Procurement Forum
Women’s Contractor Association: Luncheon/Expo
East End Chamber of Commerce: Expo/Luncheon; Small Business Development
Notes: M/WBE – Alexis Licata

## Slide 14: M/WBE commitment
Certified Minority/Women Owned Businesses Breakdown
2012 Total Combined Projects
Chart: 
| Committed MBE | Committed WBE | Non-M/WBE
2012 Total Combined Projects | 228983529 | 28055886 | 632818563
2013 Total Combined Projects | 0.2573 | 0.0315 | 0.7111
Committed WBE
$28,055,886 3.15%
Notes: M/WBE – Alexis Licata

## Slide 15: Bond financial report
The 2012 Bond Program is $1.89 billion, and the issuance of bonds is planned in four sales. Additionally, the Board of Education in 2015 approved an additional $212.4 million. Total budget is $2.1 billion.
Commitments of $889,857,978 (including encumbrances of $435,479,381 and actual expenditures of $454,378,597) leaving $1,212,591,985 of available funding.
Chart: Bond Referendum $1.89 Billion (issuance sales in millions)
 | 340 | 350 | 0 | 560
2013
(Sold Feb)
2014
(Sold Sept)
2015
2016
(Sold April)
Total Budget, Commitments & Available Funding to Date Total Budget: $2.1 billion
(issuance sales in millions)
Chart: 
| Commitments | Available to Complete Projects
Sales | 889857978 | 1212591985
Notes: Finances – Sherrie Robinson and Tonya Savoie

## Slide 16: Communications
Finalizing surveys to assess community engagement efforts
Developing communications plan for transitioning schools
Created guide for bond principals planning celebrations for project milestones
Notes: Communications – Sylvia Wood

## Slide 17: Communications
Coordinated 8 community meetings, 3 groundbreakings
Provided frequent construction updates to highlight progress
Posted regular updates to social media, blog, Facebook
Strategically pitched stories to media outlets
Notes: Communications – Sylvia Wood

## Slide 18: Looking ahead
By end of September:
  6 new schools open
  10 more contracts executed
  7 more projects under construction
Projects nearing completion:
  Sterling Aviation HS
  Delmar Fieldhouse
  Waltrip HS Renovations
Waltrip HS
Sterling HS
Notes: Looking Ahead – Derrick Sanders

## Slide 19: Thank you